## SRS Gaps
Galle Face Hotel SRS Remaining Gaps Tracker
Use this table to revise the SRS and record approvals. Close all P0 items before finalizing transactional development.
Total gaps | 32 | P0 gaps | 23 | Open gaps | 32 | Build decision | NO - P0 items remain
Priority: P0 blocks the approved build baseline. P1 must be resolved before the affected module is accepted. P2 is document-quality cleanup.
Gap ID | Priority | Area | SRS pages | Current issue | Required SRS update | Decision or input needed | Proposed owner | Development blocked | Acceptance condition | Status | Target date | Notes
GAP-01 | P0 | Document control | 1-2 | The cover, revision table and document history show conflicting versions and dates. Owner, issue date and approvals are blank. | Issue one controlled SRS version with document ID, version, issue date, owner, revision history and signed approvals. | Confirm the authoritative version and approvers. | Project Manager / SRS Author | All final development commitments | The approved document has one consistent version and completed approval records. | Open
GAP-02 | P0 | Requirement traceability | 8 and all functional sections | The SRS says every requirement has a unique ID and priority, but IDs restart at 01 and most requirements have no Must, Should or Could classification. | Assign stable requirement IDs, priority, owner, source and acceptance criteria. Add a Requirements Traceability Matrix linking design and tests. | Approve the priority model and traceability format. | Business Analyst / QA Lead | Scope control and UAT | Every Must requirement maps to design, development, test evidence and approval. | Open
GAP-03 | P0 | Deployment and tenancy | 6-7, 9, 14, 68 and 73 | The document alternates between a dedicated deployment and a shared multi-tenant platform. The current ProcureFlow baseline uses one Catalyst project per hotel group. | Select and document one model: dedicated Catalyst project per group or shared multi-customer deployment. Define organization boundaries, isolation and support access accordingly. | Architecture decision signed by client IT and implementation lead. | Client IT / Solution Architect | Data model, authentication and security | Architecture section, diagrams and NFRs describe the same approved tenancy model. | Open
GAP-04 | P0 | Organization structure | 6, 17-18 and 31-32 | Cluster, property, legal entity, department and tenant are used inconsistently, and ownership relationships are not formally defined. | Define the hierarchy, required fields, effective dates, active status, legal-entity ownership and property-to-entity mapping. | Approve the final property, cluster and legal-entity list. | Finance / Procurement / Client IT | Master data and access scope | A controlled organization data model and approved opening list are attached to the SRS. | Open
GAP-05 | P1 | Terminology and numbering | 3-5, 12-14, 51, 58 and 63 | Section numbers are duplicated or inconsistent, and terms such as vendor, supplier, tenant, cluster, bill and invoice are mixed. | Renumber the SRS and add a terminology appendix with controlled names and definitions. | Confirm preferred business terms. | SRS Author | Traceability and communication | All headings, references and defined terms are unique and consistent. | Open
GAP-06 | P0 | Expenditure categories | 21, 28, 32 and 73 | One section says three values but lists Capex, Opex, Repair and AMC. Other sections omit Repair or introduce Services. | Approve one controlled category list and use it consistently in forms, workflows, document rules, budgets and reports. | Decide whether Services is a category or a subtype and where AMC belongs. | Procurement / Finance | Forms, workflows, reports and document gates | One enumeration is used throughout the SRS and data dictionary. | Open
GAP-07 | P0 | Budget status calculation | 21-22, 58 and 62 | Requesters can select Budgeted or Non-Budgeted, while later sections say the system calculates Within Budget or Non-Budgeted. Exceeds Budget is not consistently represented. | Make budget status server-calculated. Define Within Budget, Not Budgeted and Exceeds Budget inputs, messages and workflow consequences. | Approve the controlled budget-status values. | Finance / Solution Architect | PR submission and approval routing | Boundary tests prove each status at no budget, exact balance and exceeded balance. | Open
GAP-08 | P0 | Budget ledger lifecycle | 58-62 | The SRS does not define when spend is reserved, committed, released, converted to actual or reversed. It could double-count PR, PO and invoice amounts. | Define the budget ledger, transaction timing, concurrent-spend protection, transfers, adjustments, cancellations, reversals and financial reconciliation. | Approve whether commitment occurs at submission, approval or PO issue. | Finance | Budget engine and financial reports | A complete ledger example reconciles approved, committed, actual and available balances. | Open
GAP-09 | P0 | Approval authority matrix | 29-32 | A fixed budgeted route conflicts with CAPEX, OPEX and Repair examples and entity-specific thresholds. | Replace narrative routes with one versioned authority matrix by category, budget result, value band, legal entity, property and exception type. | Provide named roles, thresholds and final authorizers. | Executive Sponsor / Finance / Procurement | Approval engine | Every route variant has an approved test case and named business owner. | Open
GAP-10 | P0 | Approval exceptions | 29-32 | Delegation, vacant roles, absence, escalation, rejection, recall, resubmission, self-approval and workflow changes during an in-flight request are incomplete. | Define allowed actions, prerequisites, comments, evidence, timeouts, segregation of duties and workflow-version snapshot rules. | Approve exception behavior for every approval stage. | Finance / Procurement / Internal Audit | Approval engine and audit | A status-transition matrix covers normal and exceptional approval paths. | Open
GAP-11 | P0 | RFQ and direct purchase | 7, 28-29 and 41 | RFQ is described as optional, but later every approved PR is converted to RFQ and a PO requires an award. | Define standard sourcing and exception routes for direct purchase, emergency purchase, contract call-off, sole source and low-value purchase. | Approve evidence and authority required for each exception. | Procurement / Finance | PR-to-PO workflow | Every PO can be traced to an awarded RFQ or an approved exception route. | Open
GAP-12 | P0 | Sealed bids | 7, 34 and 42-43 | The scope promises sealed bids, while procurement can view bids and negotiate before the RFQ closes. | Define bid encryption or access control, opening date and time, authorized opening roles, audit events, late bids and post-opening negotiation rules. | Choose the approved bid-opening model. | Procurement Committee / Internal Audit | RFQ and bid management | Tests prove bid contents cannot be viewed before the authorized opening event. | Open
GAP-13 | P1 | RFQ lifecycle | 33-43 | RFQ amendments, clarification questions, deadline extensions, timezone, cancellation after publication and submitted-bid version retention are incomplete. | Add formal RFQ and bid state machines with permitted actions, notifications and audit requirements. | Approve the official sourcing states and deadline timezone. | Procurement | RFQ workflow | State diagrams and acceptance tests cover publication through award or cancellation. | Open
GAP-14 | P0 | Required-document matrix | 32, 35, 41 and 48-50 | Document gates have improved, but categories are inconsistent and waiver, version, retention, file security and visibility rules are missing. | Create a matrix by stage, category, legal entity and value band. Define allowed types, sizes, waiver authority, retention, malware scanning and access. | Approve mandatory, conditional and waivable documents. | Procurement / Finance / Legal / Security | PR, RFQ, award, PO, receipt and invoice gates | Each missing document blocks the correct transition and every waiver is authorized and audited. | Open
GAP-15 | P0 | Supplier onboarding lifecycle | 35-40 | Registration and SCM/Finance review are defined, but more-information requests, resubmission, rejection, suspension, blacklisting, expiry and duplicate detection are missing. | Define complete supplier states, reviewer actions, resubmission rules, compliance-expiry alerts and activation prerequisites. | Approve reviewer roles and supplier-status meanings. | Supply Chain / Finance / Compliance | Supplier onboarding and portal access | The state machine covers invitation through activation, suspension or rejection. | Open
GAP-16 | P0 | Supplier credentials and bank changes | 37-39 and 69-70 | The SRS says login credentials are emailed and bank data supports EFT, but secure activation and bank-change controls are not defined. | Use single-use activation links instead of emailed passwords. Define bank-data masking, verification, change approval, dual control and audit notifications. | Approve authentication and bank-change policy. | Client IT / Finance / Security | Supplier security and payments | No password is transmitted, and bank changes require verified authorization and audit evidence. | Open
GAP-17 | P0 | Purchase-order state machine | 41, 43 and 48-51 | PO states include issued, sent, accepted, rejected, partially delivered and fulfilled, but the formal lifecycle only shows Sent to Supplier to Fulfilled. | Define all PO states and allowed actions for issue, acknowledgement, rejection, amendment, cancellation, receipt, alternate award and closure. | Approve the business owner for each transition. | Procurement / Stores / Finance | PO issue and supplier acknowledgement | A transition matrix prevents invalid or irreversible state changes. | Open
GAP-18 | P0 | Receipt and fulfillment | 49-51 | A partial receipt can refer to a Fulfilled PO. Rejected quantities may count toward Fulfilled even though they cannot be invoiced. | Add Partially Received, Received With Exception, Fulfilled and Short Closed rules. Define replacement deliveries, over-receipt tolerance, reversals and SES behavior for services. | Decide whether fulfillment requires accepted quantity or an authorized short close. | Stores / Procurement / Finance | GRN, SES, PO status and matching | Partial, rejected, replaced, over-received and short-closed scenarios produce the approved statuses. | Open
GAP-19 | P0 | Invoice matching | 52-57 | Invoice lines are defined, but tolerances, duplicate detection, partial invoices, multiple receipts, multiple invoices, freight, discounts and tax matching are incomplete. | Define line-level match calculations, cumulative quantities, tolerance configuration, discrepancy reasons, rematch and authorized override evidence. | Approve tolerance values and override authority. | Finance / Procurement | Invoice and payment control | Line-level test cases reconcile PO, GRN or SES, invoice and credits without overbilling. | Open
GAP-20 | P1 | Invoice formats and tax | 52-54 and 64 | The SRS imposes one supplier invoice-number pattern, uses MM/DD/YYYY and hard-codes 18 percent VAT while tax settings are configurable. | Store supplier references as issued, define duplicate keys, use ISO dates internally, approve display format and make tax rates effective-dated configuration. | Confirm legal tax and invoice-format requirements. | Finance / Tax Advisor | Invoice validation | Valid supplier invoices are accepted without forcing an invented number, date or tax format. | Open
GAP-21 | P0 | Payment boundary | 52-57 | The SRS mixes recording an externally executed payment with initiating electronic payment. Partial payment, authorization, failure, reversal and reconciliation rules are incomplete. | Choose Release 1 scope. If recording only, define balances and approvals. If bank initiation is included, add beneficiary verification, dual authorization, responses, failures and reconciliation. | Treasury must confirm payment execution scope and provider. | Treasury / Finance / Client IT | Payments and bank integration | Payment tests cover partial, full, overpayment, discrepancy block, override, reversal and reconciliation. | Open
GAP-22 | P0 | Integrations | 39, 63-64 and 73 | Zoho Books, WhatsApp, email and webhooks lack interface contracts, field mappings, source of truth, triggers, retry, replay, reconciliation and ownership. | Add one specification per integration covering authentication, mappings, idempotency, errors, monitoring, disconnect behavior and support ownership. | Confirm which integrations are mandatory for first release. | Client IT / Finance / Implementation Lead | External integrations | Success, duplicate, timeout, rejected payload and replay tests reconcile correctly. | Open
GAP-23 | P0 | Availability, performance and capacity | 13-14 and 68-71 | The SRS has device assumptions but no measurable availability, response-time, load, concurrency or transaction-volume targets. | State supported browsers and devices, named-user and concurrent-user volumes, annual transaction volumes, response targets and monthly availability target. | Provide expected usage and approved service levels. | Client IT / Business Owner | Architecture, testing and sizing | Performance and availability tests have measurable pass conditions. | Open
GAP-24 | P0 | Recovery, retention and monitoring | 68-71 | Backup cadence, retention, restore ownership, RPO, RTO, disaster recovery, monitoring, alerts and log retention are not defined. | Add backup and restore requirements, RPO, RTO, restore testing, monitoring, alert ownership, audit retention and incident escalation. | Approve recovery and retention targets. | Client IT / Security / Operations | Production operations | A documented restore test meets the approved RPO and RTO before go-live. | Open
GAP-25 | P1 | Identity, privacy and security | 68-71 | Server-side controls are described, but employee MFA or SSO, session duration, inactive-user handling, privacy obligations and sensitive-data retention remain undecided. | Define internal identity policy, supplier-session policy, privacy classifications, permitted uses, retention, export, correction and deletion responsibilities. | Confirm MFA, SSO and privacy requirements. | Client IT / Security / Legal | Authentication and data protection | Security tests and policy evidence cover every approved control. | Open
GAP-26 | P1 | Reports and reconciliation | 16-19 and 73 | Dashboards and reports are named generally, but columns, formulas, filters, drill-down, export, access scope, freshness and reconciliation are absent. | Create an approved report catalogue with calculation definitions and reconciliation sources. | Prioritize first-release reports and report owners. | Finance / Procurement / Management | Reporting and analytics | Each financial report reconciles to controlled source transactions. | Open
GAP-27 | P0 | Data migration | Not specified | The SRS does not define source files, cleansing, mappings, opening transactions, duplicate handling, mock loads, cutover or rollback. | Add a migration specification for users, organization data, items, suppliers, budgets, documents and open transactions, including reconciliation and sign-off. | Provide source owners, extracts and opening-balance scope. | Client Data Owners / Implementation Lead | Production readiness | At least one mock load and final reconciliation are approved before cutover. | Open
GAP-28 | P1 | Operational readiness | Not specified | Deployment environments, release approval, rollback, monitoring, training, support, incident response and hypercare are not defined. | Add an operational-readiness section with environment inventory, runbooks, support model, training and go-live exit criteria. | Name service owners and escalation contacts. | Client IT / Implementation Lead | Go-live and support | All operational deliverables are tested and handed over before production approval. | Open
GAP-29 | P0 | Acceptance and UAT | All sections | Most requirements do not have observable Given, When, Then criteria, test IDs, expected results, evidence or business approvers. | Create end-to-end UAT scenarios and acceptance criteria for every Must requirement, including negative, concurrency and authorization tests. | Approve UAT owners and production-sign-off authority. | QA Lead / Business Owners | Formal acceptance and release | All Must requirements pass traced tests or have documented accepted defects. | Open
GAP-30 | P1 | Custom modules and settings | 63-67 | The SRS allows administrators to configure arbitrary modules, workflows and fields without defining supported limits or server-side enforcement. | Limit Release 1 to named configurable fields and rules, or specify the schema builder, permission model, validations, audit and migration behavior. | Choose configuration scope for first release. | Product Owner / Solution Architect | Settings, schema and permissions | Administrators can configure only documented, tested capabilities. | Open
GAP-31 | P1 | Accessibility and compatibility | 13-15 | The SRS lists old mobile operating systems and subjective interface comments, but lacks browser versions, responsive behavior and accessibility requirements. | Define supported browsers and devices, responsive breakpoints and WCAG 2.2 AA acceptance criteria. | Approve the supported-device matrix. | Client IT / UX / QA | Frontend and browser testing | Keyboard, contrast, labeling, error and responsive tests pass on supported platforms. | Open
GAP-32 | P2 | Appendices and editorial quality | 72, 79 and 81-83 | The document contains a blank page, mismatched appendix headings or forms, duplicated wording, grammar errors and malformed table labels. | Correct appendix references, remove blank pages, proofread the document and verify that every scanned form is labeled and legible. | Confirm the authoritative version of every source form. | SRS Author | Document usability and traceability | Final PDF has correct numbering, forms, cross-references and no blank or duplicate pages. | Open
Source: Galle Face Hotel Software Requirement Specification, 84-page PDF reviewed 18 September 2026.

## Build Start
ProcureFlow Build Start Matrix
Catalyst is technically suitable. Transactional modules remain conditional on closing the related SRS gaps.
Work area | Can start now | Work allowed now | Requirement still needed | Start condition
Catalyst project setup | Yes | Confirm development project, environments, naming and deployment process. | Approved tenancy and production environment plan. | Architecture decision signed.
Authentication foundation | Conditional | Implement hosted employee authentication and basic server-side authorization. | MFA or SSO, employee session and supplier authentication decisions. | Identity policy approved.
Organization master data | Conditional | Draft organization, cluster, property, legal-entity and department tables. | Final hierarchy and opening data. | Organization model approved.
Audit framework | Yes | Create append-only business-event contract and correlation identifiers. | Final retention and export rules. | Audit event fields approved.
Document storage framework | Conditional | Create private Stratus path conventions and authorization middleware. | Document matrix, retention, malware and waiver rules. | File-security policy approved.
User-interface prototypes | Yes | Prototype forms and navigation for stakeholder review. | Final business rules and validation messages. | Prototype is explicitly non-binding.
Approval engine | No | Do not finalize route logic or schema. | Authority matrix, exceptions and workflow versioning. | GAP-09 and GAP-10 closed.
Budget engine | No | Do not finalize commitment calculations. | Budget statuses, ledger timing and concurrency rules. | GAP-07 and GAP-08 closed.
RFQ and bidding | No | Do not finalize bid visibility or award logic. | Sourcing exceptions, sealed-bid model and RFQ state machine. | GAP-11 to GAP-13 closed.
PO and receiving | No | Do not finalize status transitions. | PO, GRN, SES, rejection, replacement and short-close rules. | GAP-17 and GAP-18 closed.
Invoices and payments | No | Do not finalize matching or settlement. | Matching tolerances, payment scope, overrides and reconciliation. | GAP-19 to GAP-22 closed.
Migration and go-live | No | Start source inventory only. | Migration, operations, recovery, UAT and approval plans. | GAP-23, GAP-24 and GAP-27 to GAP-29 closed.
Current repository note: the Catalyst project is initialized. The latest verification run passed 12 of 15 stages; three browser stages could not start because the local ws test dependency is missing.